Iowa Core Curriculum Outcome 2:  Outer Circle:  Community
Community members and the other supporting agencies work together to support the implementation of the Iowa Core Curriculum.

IF multiple partners including parents, school board, business and industry, supporting agencies, and other community entitles are interdependent, THEN schools will function as an integrated system to provide a coordinated approach, consistent communication, additional opportunities for learning and the ongoing supports needed for students to be successful.
	Targets-What are we trying to accomplish
	What is the current state in our district?
	Actions-What are we going to do to reach our targets?
	Who will be responsible?
	Timelines for accomplishing this action
	Baseline Consensus Rating

	2.a. Coordination of community and other Systems to support Iowa Core Curriculum
	
	
	
	
	

	ACTION 1

2a1 Community members understand the Iowa Core Curriculum.
	Limited Knowledge:

Community members on SIAC have received the information.

Website information available.

Buzz words----cause confusion

DE---is in the process of developing information to distribute to the community


	Presentations:

SIAC

School Board

Student presentation to City Council

Publish ST/Bench

Put links on the school website

Newsletter information

Parent Teacher Conferences-info distributed

PSA on radio

CABLE TV---possible to post on them?

Website---link to Judy Jeffries videoclips

Newspaper---once a month---Algona/Humboldt


	Administrators

Technology coordinators/team/administration

Dean Bostian-Livermore

Ron Bollmeyer-GCB

Don Hasenkamp--Livermore

Tammy, Bill, Fred

Jeff Boyd
	Brochure distributed

Registration-Fall 2009

Radio:  Scripts---developed by speech/ drama kids. (BOLT 97.7 KHBT-radio in Humboldt) will work on this spring.

Livermore Cable---video—no.  Text---lines of information to put on scroll bar.

Gilmore City cable????

March----first publication
	2

	ACTION 2

2a2 Community members participate in the development & implementation of the Iowa Core Curriculum within the district
	No input at this point.
	Develop a Key Survey to send to the businesses to provide us information

Business and Industry information on 21st Target the 21st Century Skills to gather community input
	Jeff B. will collect e-mail addresses of Businesses when the kids sell Yearbook ads.

Ron will convey information to Humboldt/Fort Dodge businesses

Job Fair attend??

Student Council go to City Council meeting to present the information to them and have them collect e-mail addresses
	List compiled…. Intent of Key Survey:  incorporate resources to help us implement:

Employability/support curriculum/preparedness of students. (FORUM w/Algona & Humbolt businesses…FALL 2009)

(Job Fair??)

Website PLEA

2010-2011
	1

	ACTION 3
2a3 Learning supports are coordinated to support the Iowa Core Curriculum


	AEA staff/DE consultants/TRV-ICC Leadership Team


	Attend meetings
	Team
	
	

	2a4 Involvement in the school board in implementing the Iowa Core
	Board wishes to stay informed and will provide input as necessary.
	Keep the board informed monthly about where we are going .
	Principals
	Monthly
	

	Learning Supports are coordinated to support the Iowa Core Curriculum
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	


1


TRV 1-7-09 tjj


